UMER

Full-Stack Developer — Mobile & Web Applications

Prepared for:	Anouar

Market:	Morocco

Date:	21 June 2026

PROJECT PROPOSAL

Free-Floating Rent-A-Car Platform — Morocco Launch

Price, Timeline & Project Requirements

# 1. Project Summary

Anouar has confirmed this platform will launch in Morocco. This proposal covers the full platform in one phase: the customer mobile app (iOS and Android), the web admin panel (called “Control Tower”), the backend system, the GPS/IoT integration, payments, geofencing, and dispute handling.

# 2. Price

Total fixed price: $7,500 USD

Payment is split into 5 milestones. Each milestone is only paid after that part of the work is shown and approved.

| Milestone | What is delivered | % of total | Payment |
| --- | --- | --- | --- |
| M1 — Planning (Week 1-2) | System design, database plan, API plan, project setup, and a first test with the GPS vendor's API | 20% | $1,500 |
| M2 — Backend + Admin basics (Week 3-5) | Login system, ID verification process, vehicle management, geofencing (virtual zones), live map | 25% | $1,875 |
| M3 — Mobile app main screens (Week 6-8) | Sign-up, map to find cars, booking flow, unlock-by-proximity screen, active trip screen | 25% | $1,875 |
| M4 — GPS/IoT, payments & admin tools (Week 9-10) | Connect to vendor's GPS system, payment and deposit flow, pricing rules, dispute tool | 20% | $1,500 |
| M5 — Testing & launch (Week 11-12) | Full testing, fixing issues, going live, handover documents | 10% | $750 |

- This price covers development only. It does not include app store fees (Apple: $99/year, Google: $25 one-time), server/hosting costs, SMS costs, or payment gateway fees. These are paid by Anouar directly, using Anouar's own accounts.

- After final delivery, there is a 2-week free support period to fix any bugs. Any support needed after that is a separate monthly agreement.

# 3. Timeline

Target: 11-12 weeks (about 2.5 to 3 months) from the start date.

- Anouar has confirmed that the GPS tracking / IoT system will be purchased from a separate hardware vendor. This timeline assumes the vendor gives full API documentation and a test device by the end of Week 1. If the vendor is late, or the documentation is incomplete, the GPS/IoT-related milestone (M4) will be delayed by the same amount of time.

- This timeline also assumes Anouar reviews each milestone and gives feedback within 48 hours. Slower feedback will extend the timeline.

- App store review time (Apple usually takes 1-3 days) happens at the end and is not something the developer can control.

# 4. What's Included

- Customer mobile app for iOS and Android, built from one codebase: sign-up, ID verification, map to find cars, booking, unlock-by-proximity, active trip screen, return checklist

- Web admin panel: live map of all cars, vehicle and driver management, ID document review, pricing and penalty rules, dispute/claims tool

- Backend system: API, database, login system, geofencing (virtual zones on the map), and handling data sent from the GPS/IoT devices

- GPS/IoT integration: sending unlock/lock commands to the car, receiving live location and status data, and a backup method (Bluetooth) for areas with no signal — the exact scope depends on what the vendor's API actually supports

- Payment integration: saving card details safely, holding and charging the security deposit, and creating invoices automatically

- Putting the app and system live, plus basic documentation explaining how everything works

# 5. What I Need From Anouar

These items are required to start the project and to keep the timeline above. Without them, work cannot begin or will be delayed.

| # | What I need from Anouar to start, or during the project |
| --- | --- |
| 1 | CONFIRMED: Anouar is buying the GPS tracking / IoT hardware system. Still needed: the vendor's name, full API documentation, and login details for a test device. This is the most important item — if it is late or incomplete, the whole timeline is affected |
| 2 | A payment provider account (test and live keys) once the provider is chosen |
| 3 | A Google Maps API key (or another mapping service if preferred) |
| 4 | An SMS provider account (such as Twilio or a local provider) to send verification codes |
| 5 | An Apple Developer account and a Google Play Console account, owned by Anouar — apps will be published under Anouar's own accounts, not mine |
| 6 | A domain name and server/hosting access (or a budget so I can set this up and recommend an option) |
| 7 | Brand materials: logo, brand colors, app name, and any existing marketing text |
| 8 | A sample list of vehicles: model, category, plate number, and pricing if already decided |
| 9 | Basic legal/business information needed for the in-app terms of service, privacy policy, and insurance information |
| 10 | One main contact person for weekly check-ins, who can give feedback quickly — slow feedback will delay the project |

# 6. Questions to Confirm With Anouar

Please confirm the answers to these questions before the project starts. This helps avoid delays or misunderstandings later.

| # | Question to confirm with Anouar |
| --- | --- |
| 1 | Which city should the service start in — one city only (for example Casablanca), or more than one city from the beginning? |
| 2 | How many cars will be in the starting fleet, and what models/types? |
| 3 | Anouar has confirmed they will purchase the GPS/IoT hardware system. Which vendor/brand is it, and when will the API documentation and a test device be ready? |
| 4 | Which payment provider should be used — a local Moroccan provider (like CMI) or an international one (like Stripe)? Should the app also support cash or mobile wallet payments, not just cards? |
| 5 | Which languages does the app need to support — Arabic, French, English? Which one is the main language? |
| 6 | Who will check and approve the uploaded ID documents — Anouar's own team, or should this be fully automatic? |
| 7 | Is there already an insurance company working with Anouar? Do they have specific rules that affect deposits or penalties? |
| 8 | Who decides the exact zones on the map where cars can be picked up, dropped off, and parked? Is this information ready? |
| 9 | How should customers get help during a trip if something goes wrong — in-app chat, a phone number, or both? |
| 10 | Does Anouar already have a business name, logo, and brand colors, or is this something I need to help create? |

# 7. Payment Terms

- Payment for Milestone 1 is due before work starts. Each milestone after that is due within 3 business days of approval.

- Each milestone is shown to Anouar (live call or recorded video) before the next milestone begins.

- Any new feature or change requested after a milestone is approved will be priced separately. It will not be taken from the budget of the remaining milestones.